CLUB OS

30-Day Build Plan

From prototype to a working, deployable operations platform

Golf operations · Tournaments · Pro shop · Caddies · Tee times

Target: country clubs and their head pros & general managers

# Before Day 1: What This Plan Is (and Isn't)

The goal: a real, working application that a single pilot country club can run their daily golf operations on by day 30 — not another clickable demo. That means a real database, real user accounts, data that persists, and a version deployed to the web that staff can log into from the pro shop counter.

Honest scope note. A full multi-club commercial SaaS — with payment processing, GHIN handicap integration, hardware POS, and multi-tenant billing — is a 6–12 month effort for a team. Thirty days by one focused builder (with AI pair-programming) buys you a genuinely functional single-club v1 covering the operational core: tee sheet, tournaments, pro shop, caddies, and members. That is exactly the right first milestone: something a friendly pilot club uses for real, which becomes your proof and your feedback engine.

What is deliberately deferred to post-30-days: online member self-service, real card payments, GHIN, multi-club tenancy, native mobile apps. Each is noted in the roadmap at the end so you can speak to it credibly in a pitch without over-promising.

## The Guiding Principle

Every day of this plan ends with something that works and is checked in. No big-bang integration at the end. By building thin vertical slices — one real feature, database to screen, working end-to-end — you always have a demoable, deployable app. If day 30 arrives early or late, you still have a coherent product at whatever line you stopped on.

# The Technology Stack

Chosen for speed of solo development, low operational cost, and being genuinely productionizable — not throwaway. All of it has strong AI-assistant support, which matters when you're the only developer.

| Layer | Choice | Why |
| --- | --- | --- |
| Framework | Next.js (React) + TypeScript | One codebase for UI and backend API routes. You already think in React from the prototype — this is a direct upgrade path, not a rewrite. |
| Database | PostgreSQL (via Supabase) | Real relational DB with a generous free tier. Supabase also gives you auth and a hosting dashboard out of the box, removing a week of setup. |
| Auth | Supabase Auth | Email/password logins and roles (GM, head pro, pro shop, caddie master) without building auth from scratch. |
| ORM | Prisma | Type-safe database access. Define your schema once; it generates the query layer. Fast to iterate. |
| Styling | Tailwind CSS | Keeps the clubhouse-ledger aesthetic you've already designed, at speed. |
| Hosting | Vercel | Push to GitHub, auto-deploys. Free tier is enough for a pilot. Live URL from day one. |
| Text / SMS | Twilio (deferred wiring) | Tournament field texts. Account set up early, real send left to week 4 to control cost. |

If you'd rather not learn Next.js, the same plan works with a plain React front end + a small Node/Express API. The day-by-day milestones don't change — only the file layout does.

# The 30 Days at a Glance

| Week | Theme | End-of-week outcome |
| --- | --- | --- |
| Week 1 (Days 1–7) | Foundation & Tee Sheet | Deployed app with real login and roles. Tee sheet works end-to-end against the database — book, edit, assign a caddie, and it persists. |
| Week 2 (Days 8–14) | Members, Pro Shop & POS | Member directory backed by real data. Pro shop inventory with a working point-of-sale that charges to member accounts and posts to their balance. |
| Week 3 (Days 15–21) | Caddies & Tournaments | Caddie program with assignment and loop tracking. Tournament Ops built for real: pairings, flights, live scoring, payouts. |
| Week 4 (Days 22–30) | Tournament comms, polish, pilot | Field texts (real SMS), weather/rulings/sponsor logs, the operations dashboard, hardening, and a real pilot club onboarded. |

# Week 1 — Foundation & Tee Sheet

Why this first: the tee sheet is the heartbeat of daily golf ops and the single feature staff touch most. Getting it working against a real database — with login and roles — proves the entire architecture end-to-end and gives you something a club can react to immediately.

### Day 1 — Project spine

- Create the GitHub repo, scaffold the Next.js + TypeScript app, deploy the empty shell to Vercel so you have a live URL on day one.

- Stand up the Supabase project (database + auth). Connect Prisma. Confirm you can read/write one test row from the deployed app.

- End of day: a deployed, empty app that talks to a real database.

### Day 2 — Auth & roles

- Implement email/password login. Seed four user accounts: GM, Head Pro, Pro Shop, Caddie Master.

- Build the role system so each role sees the right navigation (port the ROLES logic from the prototype).

- End of day: you can log in as any role and see a correctly filtered (empty) shell.

### Days 3–4 — Data model & the shell UI

- Design the core schema: clubs, users, members, tee_slots, caddies, inventory, sales, tournaments, and their child tables. Get this right now — it underpins everything.

- Port the visual design system (sidebar, top bar, the parchment/hunter/brass aesthetic) into Tailwind components so every later feature inherits the look for free.

- End of day 4: the app looks like your prototype and has a real, migrated schema behind it.

### Days 5–7 — Tee Sheet, end-to-end

- Build the tee sheet reading real slots from the database for a chosen date.

- Booking flow: click a slot → assign a group, walking/cart, and a caddie → saves and persists.

- Add the day switcher (real dates, real data per day) and block/maintenance slots.

- End of week 1: a logged-in staff member can manage a real tee sheet that survives a refresh and is live on the web. This is your first genuinely useful feature.

# Week 2 — Members, Pro Shop & Point of Sale

Why this next: the pro shop touches money, and 'does it actually ring up a sale and post it to the member's account' is the question that most often decides these deals. Members underpin both the POS and, later, tournaments.

### Days 8–9 — Member directory

- CRUD for member households: type, family size, standing, dues status, join date.

- Member detail view — click a household to see their profile, dues, and activity (this was a gap in the prototype).

- Import: let a club load their existing membership from a CSV, so onboarding a pilot is realistic.

### Days 10–12 — Pro shop inventory & POS

- Inventory CRUD with categories, price, stock on hand, and reorder points with automatic low-stock flags.

- Point of sale: pick items, set quantity, choose walk-in/cash or charge-to-member, complete the sale — decrement stock atomically.

- Charge-to-member posts to that member's running balance and appears on their profile. This is the integration moment that sells the platform story.

### Days 13–14 — Sales history & member billing view

- Recent-sales log and a simple per-member statement (month-to-date charges).

- Basic daily sales summary for the pro shop.

- End of week 2: staff can manage members, run the pro shop register, and see charges flow onto member accounts — a connected system, not separate screens.

# Week 3 — Caddies & Tournament Operations

Why this next: caddie management is a real daily pain point clubs handle badly, and tournament ops is your sharpest differentiator versus dated incumbents. Both are where a head pro feels the value immediately.

### Days 15–16 — Caddie program

- Caddie roster with tiers (looper / standard / tournament) and daily availability status.

- Assign caddies to tee times (ties into week 1's tee sheet) and track loops per day.

- Loop-fee / pay tracking per caddie — a concrete feature incumbents often lack.

### Days 17–18 — Tournament setup: pairings & flights

- Create a tournament: name, date, format, shotgun or tee-time start.

- Build the field, assign players to flights, and generate pairings by starting hole.

### Days 19–21 — Live scoring & payouts

- Live leaderboard: enter/adjust scores and thru-holes per group; auto-sort within flights.

- Payout structure by flight and place, with paid/pending tracking.

- End of week 3: a head pro can run a real tournament start to finish — field, flights, live scores, and prize money — plus manage caddies against the live tee sheet.

# Week 4 — Tournament Comms, Polish & Pilot Launch

Why this last: these features make the product feel alive and trustworthy, and the final days are reserved for the unglamorous, essential work of hardening and getting a real club actually using it.

### Days 22–23 — Field communications (real SMS)

- Wire Twilio to broadcast text updates to a tournament field; log every message sent.

- Weather-delay controls (active / delay / suspended) that timestamp and log automatically, and can trigger a field text.

### Days 24–25 — Rulings & sponsors

- Rules-decision log (hole, ruling, official, timestamp) for the record and pace-of-play.

- Sponsor contact list with outreach logging for the event.

### Day 26 — Operations dashboard

- The cross-module overview: rounds booked, caddies on loop, low-stock flags, active members, and a live alerts feed — now reading real data from every module.

### Days 27–28 — Hardening

- Input validation, error states, empty states, loading states. Permission checks enforced on the server, not just hidden in the UI.

- Test on a phone and a tablet — the pro shop counter and the course starter will not be at a desktop.

- Back up the database; confirm a restore works.

### Days 29–30 — Pilot onboarding

- Load a real pilot club: their members (CSV import), their tee sheet intervals, their inventory, an upcoming event.

- Sit with the head pro or GM for a live run-through; capture the first feedback list.

- End of day 30: a real club is running real daily operations on the app. That is the milestone — a working product with a live user, not a demo.

# Where This Plan Could Slip — and How to Protect It

| Risk | Mitigation |
| --- | --- |
| Scope creep — 'just one more feature' | The schema and week themes are fixed. New ideas go on the post-30 roadmap, not into the sprint. A working narrow app beats a broken broad one. |
| A single day runs long and cascades | Each day ships something working and checked in. If you fall behind, cut depth within a feature (fewer fields), never skip the end-to-end slice. |
| Auth / data-model rework mid-build | Spend the time on the schema in days 3–4. Changing the data model in week 3 is the most expensive mistake available; changing UI is cheap. |
| Learning-curve on a new stack | Days 1–2 are deliberately light on features and heavy on setup for exactly this reason. If the stack fights you, fall back to plain React + Node — milestones unchanged. |
| Payments / GHIN pressure from a prospect | These are explicitly post-30. Have the roadmap ready so you can say 'here's exactly when and how' rather than bolting them in half-done. |

## Definition of Done for v1

- Deployed to a live URL a club can reach.

- Real login with four working roles.

- Persistent data — nothing resets on refresh.

- Five operational cores working end-to-end: tee sheet, members, pro shop + POS, caddies, tournaments.

- One real pilot club using it for daily operations.

# After Day 30: The Roadmap

Sequenced by what turns a working single-club tool into a sellable multi-club product. Share this selectively with prospects to show the trajectory without over-promising the present.

### Phase 2 (Months 2–3) — Commercial readiness

- Multi-club tenancy — one deployment serving many clubs with isolated data.

- Real card payments (Stripe) alongside charge-to-account.

- Member self-service: a member-facing portal to book tee times and view statements.

- Reporting with real historical trends and exports.

### Phase 3 (Months 4–6) — Depth & integrations

- GHIN / handicap integration for tournaments.

- F&B / dining reservations module.

- Native or installable mobile app for starters and caddie masters on the course.

- Accounting export (QuickBooks) for the back office.

Build one thing that works, get one club to love it, and let their feedback — not a feature list — drive what comes next.